## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 27
PROJECT NAME | Chat Based Form Filler
PROJECT MENTOR (sponsor) | Akhila Veningaya
TEAM MEMBERS | Kausheya Roy
Hemang Joshi
Shubhan Biswas
Hari Akash K
Neha Prabhu

## Status
PROJECT NUMBER | 27
PROJECT NAME | Chat Based Form Filler
PROJECT MENTOR (sponsor) | Akhila Veningaya
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Kausheya | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Hemang | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting | Requirements | Shubhan | 1 | 2 | Done | Get a running demo within 10 days. | -1 | 50
Project synopsis writeup | Documentation | Hari Aakash | 1 | 1.2 | Done |  | -0.2 | 16.6667
Team Meeting | Requirements | Neha | 1 | 2 | Done |  | -1 | 50
Week 2 (January 22 - January 28)
Team Meeting | Coordination | Hemang | 0.5 | 0.3 | Done
Draft initial pipeline | Design | Hari Aakash | 4 | 2 | Done |  | 2 | 100
Make a demonstration video | Development | Shuban | 1 | 1.5 | Done |  | -0.5 | 33.3333
Present video to Client | Testing | Kausheya | 1.5 | 0.5 | Done |  | 1 | 200
Status tracker | Documentation | Neha | 3 | 1 | Done |  | 2 | 200
Week 3 (January 29 - February 4)
Setup Basic UI Layout | Development | Shuban | 1 | 2 | Done |  | -1 | 50
Improve Pipeline | Development | Hemang | 3 | 3 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
Add a summarizer | Development | Kausheya | 2 | 1.5 | Done |  | 0.5 | 33.3333
Add logging functionalities | Development | Neha | 2 | 1.5 | Done |  | 0.5 | 33.3333
Conversation & Form Fill UI | Development | Hari Aakash | 1.5 | 1.5 | Done |  | 0 | 0
Client meeting | Coordination | Shubhan | 2 | 1 | Done | Was cancelled, but work was delivered.
Week 4 (Februrary 5 - Februray 11)
implement conversation edit, refine UI and persistence | Development | Neha | 5 | 4 | Done |  | 1 | 25
Internal team meeting | Coordination | Hemang | 2 | 3 | Done |  | -1 | 33.3333
Implement Chunking | Development | Kausheya | 3 | 3.5 | Done |  | -0.5 | 14.2857
setup data generation pipeline | Development | Shuban | 4 | 4.5 | Done |  | -0.5 | 11.1111
setup FunctionGemma | Development | Hari Aakash | 5 | 5.2 | Done |  | -0.2 | 3.8462
Week 5 (February 12 - February 18)
Implement Conversation Summarizer | Development | Neha | 2.5 | 2.8 | Done |  | -0.3 | 10.7143
Internal team meeting | Coordination | Shuban | 1.5 | 1 | Done |  | 0.5 | 50
Architecture Diagram | Design | Neha | 1.2 | 1 | Done |  | 0.2 | 20
Data Generation | Development | Shuban | 4.5 | 4 | Ongoing |  | 0.5 | 12.5
Train Model Based on the Architecture Diagram | Development | Hari Aakash | 4.5 | 2.75 | Ongoing |  | 1.75 | 63.6364
Added Bubbled conversation in create / edit conversation + UI styling update | Development | Kausheya | 2.5 | 3.8 | Done |  | -1.3 | 34.2105
Setup Dynamic Inference Pipeline | Development | Hemang | 2 | 1.5 | Ongoing |  | 0.5 | 33.3333
SRS | Documentation | Team | 4 | 5.2 | Done |  | -1.2 | 23.0769